## Instructions
Weekly Team Meeting Agenda: How to Use
A weekly team meeting that has no agenda runs long, drifts off-topic and ends with nobody sure who
does what next. This template gives you a time-boxed agenda that keeps the meeting on the clock, and
an action tracker that carries every decision forward with an owner and a due date. Built for Indian
restaurants, retail, factories, clinics, warehouses, salons, hotels and offices.
SHEETS IN THIS WORKBOOK:
1. Instructions (this sheet)
2. Weekly Agenda: a time-boxed running order; the Start and End clock times fill in automatically
3. Action Items Tracker: every task from the meeting, with an auto OVERDUE / DUE THIS WEEK / DONE status
4. Industry Agenda Variants: ready agenda focus, metrics and timing for 10 kinds of business
5. Meeting Log & Attendance: a record of each meeting, attendance percentage and decisions
6. Dashboard: live counts of open, overdue and done actions, plus average attendance
STEP-BY-STEP:
Step 1: Fill the Team Roster on the 'Action Items Tracker' (cream cells, columns K-L). Add each
team member once. The Owner dropdowns on the Agenda and Action Items pick from this list.
Step 2: Open 'Weekly Agenda'. Enter the meeting date and a Start Time, then list the agenda items
with a duration in minutes for each. The Start and End clock times calculate themselves, so
you can see exactly when the meeting will finish and keep each item to time.
Step 3: During the meeting, add every task to 'Action Items Tracker'. Pick the owner, set a due date
and a priority. The Status shows OVERDUE (red), DUE THIS WEEK (amber), OPEN (blue) or DONE
(green) on its own, and refreshes every time you open the file. Mark Done? = Yes when finished.
Step 4: After the meeting, add a row to 'Meeting Log & Attendance' (date, invited, present, decisions).
The attendance percentage calculates for you. Check the 'Dashboard' any time.
RUN A TIGHT MEETING:
Start on time, follow the running order, and end every item with a clear action, an owner and
a due date, never 'someone should look into this'. Review last week's open actions first, so
nothing quietly drops. The 'Industry Agenda Variants' sheet suggests what to focus on by trade.
FORMAT: Dates are DD-MMM-YYYY. Times use a 12-hour clock. Attendance is a percentage. 'Due this week'
means the due date is within the next 7 days.
NEED MORE ROWS? This template holds 20 agenda items, 40 action items and 30 logged meetings.
To add more: go Review > Unprotect Sheet, insert rows inside the table, then drag the formula
cells (Start, End, Days Left, Status, Attendance %) down into the new rows.
Powered by Petpooja Tasks: assign each action to a person, auto-remind them on WhatsApp, and get
photo, video or audio proof when it is done. petpooja.com/tasks

## Weekly Agenda
Weekly Team Meeting Agenda
Enter a Start Time and a duration for each item; the Start and End clock times fill in automatically. Keep to the times and the meeting ends when it should.
| Week of: | 2026-07-13 |  | Facilitator: | Store Manager
| Meeting Date: | 2026-07-14 |  | Note-taker: | Shift Supervisor
| Start Time: | 10:00 |  | Location / Mode: | Back office / Google Meet
# | Agenda Item | Category | Owner | Duration (min) | Start | End | Discussion Notes / Decisions
1 | Check-in and round-the-table | Check-in | Store Manager | 5 |  |  | Quick status from each person
2 | Review last week's action items | Review | Shift Supervisor | 10 |  |  | Close what is done, chase what is open
3 | Key numbers this week (sales, footfall, tickets) | Metrics | Store Manager | 10 |  |  | Compare with target and last week
4 | Wins and recognition | Wins | Store Manager | 5 |  |  | Call out good work by name
5 | Blockers and issues to resolve | Blockers | Shift Supervisor | 10 |  |  | One owner per blocker
6 | This week's top priorities | Priorities | Store Manager | 8 |  |  | Pick 3, not 10
7 | New action items and owners | Actions | Shift Supervisor | 5 |  |  | Log each in the Action Items tab
8 | Announcements (roster, offers, policy) | Announcements | Store Manager | 4 |  |  | Keep it short
9 | Wrap-up and next meeting time | Wrap-up | Store Manager | 3 |  |  | Confirm date and owners
10
11
12
13
14
15
16
17
18
19
20
|  |  | TOTAL / ENDS AT |  | Ends at →
Powered by Petpooja Tasks: recurring agendas, WhatsApp reminders, proof of completion. petpooja.com/tasks

## Action Items Tracker
Action Items Tracker: every task the meeting agreed
Log each action, pick an owner, set a due date. The Status flags OVERDUE, DUE THIS WEEK, OPEN or DONE for you, and refreshes every time you open the file.
# | Action Item | Owner | Raised On | Due Date | Priority | Done? | Days Left | Status | Team Member | Role
1 | Fix slow thermal printer at billing counter 2 | Rahul (Store In-charge) | 2026-07-07 | 2026-07-11 | High | No |  |  | Store Manager | Owner / Manager
2 | Reorder low-stock fast-movers before the weekend | Priya (Purchase) | 2026-07-08 | 2026-07-18 | High | No |  |  | Shift Supervisor | Operations
3 | Publish next week's staff roster on the group | Store Manager | 2026-07-08 | 2026-07-16 | Medium | No |  |  | Anjali (Cashier) | Billing / Accounts
4 | Follow up pending payment with vendor Mapro | Vikram (Accounts) | 2026-07-01 | 2026-07-09 | Medium | Yes |  |  | Rahul (Store In-charge) | Stock / Store
5 | Train new cashier on the billing shortcuts | Store Manager | 2026-07-07 | 2026-07-23 | Medium | No |  |  | Priya (Purchase) | Purchase / Vendors
6 | Resolve AC complaint in the seating area | Rahul (Store In-charge) | 2026-07-09 | 2026-07-12 | High | No |  |  | Vikram (Accounts) | Accounts / Compliance
7 | Collect and file customer feedback forms | Sana (Floor Staff) | 2026-07-08 | 2026-07-25 | Low | No |  |  | Sana (Floor Staff) | Floor / Service
8 | Renew the FSSAI display licence board | Vikram (Accounts) | 2026-07-05 | 2026-08-04 | Medium | No |  |  | Imran (Kitchen/Prod. Head) | Kitchen / Production
9 | Deep-clean the store room and re-label racks | Sana (Floor Staff) | 2026-07-03 | 2026-07-10 | Low | Yes
10 | Update Google Business profile hours | Priya (Purchase) | 2026-07-09 | 2026-07-30 | Low | No
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Powered by Petpooja Tasks: recurring agendas, WhatsApp reminders, proof of completion. petpooja.com/tasks
Formulas:
Days Left = IF([Due Date]="","",IF([Done?]="Yes","",[Due Date]-TODAY()))
Status = IF([Due Date]="","",IF([Done?]="Yes","DONE",IF([Due Date]<TODAY(),"OVERDUE",IF([Due Date]-TODAY()<=7,"DUE THIS WEEK","OPEN"))))

## Industry Agenda Variants
Weekly Meeting Agenda, by Industry
A starting focus for the weekly huddle in ten kinds of Indian SME. Copy the items that fit onto the 'Weekly Agenda' sheet and set your own timings.
Industry | Weekly meeting focus | Key metrics to review | Cadence | Duration
| Restaurant / QSR | Yesterday and last week's covers, table turnaround, kitchen delays, customer complaints, upcoming reservations and events | Sales vs target, average bill, food cost %, Swiggy/Zomato ratings | Weekly + daily 10-min | 45-60 min
| Retail store | Footfall and conversion, fast and dead stock, billing queue times, upcoming offers, shrinkage and returns | Sales/sq ft, conversion %, stock cover, top/bottom SKUs | Weekly | 45 min
| Manufacturing unit | Production vs plan, machine downtime, rejections and rework, safety incidents, raw-material availability | Output vs plan, rejection %, OEE, on-time dispatch | Weekly + daily shift | 45-60 min
| Warehouse / Logistics | Dispatch accuracy, pending orders, vehicle availability, damages, returns and RTOs, route delays | On-time dispatch %, order accuracy, cost per delivery | Weekly + daily | 30-45 min
| Hospital / Clinic | Patient load, OPD/IPD flow, complaints, equipment status, pharmacy stock, staff roster and leave | Bed occupancy, avg wait time, patient feedback score | Weekly | 45 min
| Salon / Spa | Bookings and no-shows, service mix, product retail sales, staff utilisation, customer feedback | Revenue per chair, rebooking %, membership sales | Weekly | 30-45 min
| Hotel | Occupancy and ADR, guest feedback, housekeeping turnaround, F&B covers, maintenance and safety | Occupancy %, ADR, RevPAR, review score | Weekly + daily briefing | 45-60 min
| Corporate office | Project and deliverable status, blockers, client updates, hiring, facilities and IT issues | Milestones on track, open tickets, utilisation | Weekly | 45-60 min
| Cloud kitchen | Orders by brand and aggregator, prep times, packaging errors, rider wait, menu and pricing | Orders/brand, avg prep time, rating, cancellation % | Weekly + daily | 30-45 min
| Construction site | Work vs schedule, material and labour availability, safety toolbox review, quality snags, RA-bill status | Progress vs plan, safety incidents, material stock | Weekly + daily toolbox | 45 min
Pair the weekly meeting with a daily huddle in fast-moving trades. Petpooja Tasks can push a recurring agenda and reminders to the whole team on WhatsApp. petpooja.com/tasks

## Meeting Log & Attendance
Meeting Log & Attendance: a record of every huddle
Log each meeting after it ends. Attendance percentage calculates from Present divided by Invited.
# | Meeting Date | Facilitator | Invited | Present | Attendance % | Actions Raised | Actions Closed | Key Decisions
1 | 2026-07-14 | Store Manager | 10 | 9 |  | 6 | 3 | Approved weekend offer; new cashier training this week
2 | 2026-07-07 | Store Manager | 10 | 8 |  | 5 | 4 | Shifted purchase day to Tuesday; printer AMC to be renewed
3 | 2026-06-30 | Shift Supervisor | 10 | 10 |  | 4 | 4 | Extended evening shift by 30 min for month-end rush
4 | 2026-06-23 | Store Manager | 10 | 7 |  | 6 | 5 | New vendor for packaging approved on trial
5 | 2026-06-16 | Store Manager | 10 | 9 |  | 5 | 3 | Feedback QR code to be put on every bill
6 | 2026-06-09 | Shift Supervisor | 10 | 8 |  | 5 | 5 | Reworked the opening checklist after two late openings
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
AVERAGE / TOTAL
Powered by Petpooja Tasks: recurring agendas, WhatsApp reminders, proof of completion. petpooja.com/tasks

## Dashboard
Meeting & Action Dashboard
Live rollup of the Action Items Tracker and Meeting Log. Updates every time you open the file.
ACTION ITEMS (live) | MEETINGS
OVERDUE | Meetings logged
DUE THIS WEEK (<=7 days) | Average attendance
OPEN | Actions raised (logged)
DONE | Actions closed (logged)
Total action items
FOLLOW-THROUGH
Action close rate (logged)
Actions still to close
Every action needs an owner and a reminder, or it dies in the notes. Petpooja Tasks assigns each task, nudges the owner on WhatsApp, and asks for proof when it is done. petpooja.com/tasks